## Defect mngt data
Key | Detection phase | Injection phase | Created | Severity | Status | Issue Type | Summary | Assignee | Reporter | Priority | Resolution | Updated
ORC-15394 | System Exploitation | Coding | 17/08/11 | Minor | Closed | Problem Report | ConnectorIVV: fix phases and contexts count | orchestra the standard user for orchestra test |  |  |  | 22/08/11
ORC-15223 | Coding | Coding | 02/08/11 | Minor | Closed | Problem Report | Context Contribution jar file is not copied and used properly | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-15208 | Software Unitary Tests | Coding | 01/08/11 | Minor | Closed | Problem Report | Generated ConnectorIVV...msi does not create the contribution jar file and the link file in the proper locations | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-15205 | System Exploitation | Coding | 01/08/11 | Blocking | Closed | Problem Report | Extracted labels for Contexts are invalild if Phases exist | orchestra the standard user for orchestra test |  |  |  | 23/08/11
ORC-15192 | Coding | Coding | 29/07/11 | Minor | Closed | Enhancement Request | damn py file won't work | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-15186 | Coding | Coding | 29/07/11 | Minor | Closed | Enhancement Request | py file modification | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-15185 | Coding | Coding | 29/07/11 | Minor | Closed | Enhancement Request | new python file modification | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-15180 | Coding | Coding | 28/07/11 | Minor | Closed | Enhancement Request | modifying the python file to move our jar file | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-15174 | Coding | Coding | 28/07/11 | Minor | Closed | Enhancement Request | Modified ConnectorIVV | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-15145 | Coding | Coding | 26/07/11 | Minor | Closed | Enhancement Request | ConnectorIVV: add PDE plugin for default context customizatrion | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-15144 | Coding | Coding | 26/07/11 | Minor | Closed | Enhancement Request | Adding a PDE job in order to be able to generate a new Orchestra IVV context at will | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-15117 | Coding | Coding | 25/07/11 | Minor | Closed | Problem Report | changes | orchestra the standard user for orchestra test |  |  |  | 22/08/11
ORC-15114 | Coding | Coding | 25/07/11 | Minor | Closed | Problem Report | Changing the damn vbproj file | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-15112 | Coding |  | 25/07/11 | Minor | Closed | Problem Report | changing the damn vbproj file | orchestra the standard user for orchestra test |  |  |  | 09/08/11
ORC-15111 | Coding | Coding | 25/07/11 | Minor | Closed | Problem Report | chaging the vbproj file after file modification | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-15110 | Coding | Coding | 25/07/11 | Minor | Closed | Enhancement Request | IVV Connector modification after data model changes | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-15109 | Coding | Coding | 25/07/11 | Minor | Closed | Enhancement Request | IVV Connector modifications for new datamodel | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-15086 | Coding | Coding | 20/07/11 | Minor | Closed | Enhancement Request | Migration tool UI change | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-15085 | System Experimentation | Coding | 20/07/11 | Minor | Closed | Problem Report | version.txt is bundled in the ConfdirIIVV archive | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-15083 | Coding | Coding | 19/07/11 | Minor | Closed | Enhancement Request | Adding a version.txt file for the IVV Confdir | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-15044 | Coding | Proposal | 13/07/11 | Minor | Closed | Enhancement Request | Adding new files for IVV Management packaging | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-15037 | Coding | Coding | 12/07/11 | Minor | Closed | Enhancement Request | removing unnecessart Confdir files | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-15035 | Coding | Coding | 12/07/11 | Minor | Closed | Problem Report | Branch to merge | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-15028 | Coding | Coding | 12/07/11 | Minor | Closed | Enhancement Request | Removing useless Excel dependencies | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-14550 | Coding | Coding | 25/05/11 | Minor | Closed | Enhancement Request | Modifying the connector, again. | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-14535 | Software Unitary Tests | Coding | 25/05/11 | Minor | Closed | Problem Report | Mozart needs column sizes in generated gef files, this data is lacking | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-14496 | System Factory Validation |  | 20/05/11 | Major | Analysed | Enhancement Request | Publication context creation for the IVV artifacts | orchestra the standard user for orchestra test |  |  |  | 04/08/11
ORC-14276 | System Site Integration |  | 05/05/11 | Minor | Closed | Problem Report | Connection between IVV excelsheet and Orchestra | orchestra the standard user for orchestra test |  |  |  | 04/08/11
ORC-14272 | Software Integration | Software Integration | 05/05/11 | Major | Closed | Problem Report | Error on Step type description | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-14255 | Coding | Software Integration | 04/05/11 | Minor | Closed | Problem Report | Replace file | orchestra the standard user for orchestra test |  |  |  | 22/08/11
ORC-14254 | Coding | Coding | 04/05/11 | Minor | Closed | Problem Report | Catch IVV test sheet version test | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-14233 | Other | Coding | 03/05/11 | Minor | Closed | Problem Report | ConnectorIVV version compatibility | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-14232 | System Specification | Coding | 03/05/11 | Minor | Closed | Enhancement Request | Updating the IVV connector to handle XML files | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-14211 | Software Integration | Coding | 02/05/11 | Minor | Closed | Problem Report | ConnectorIVV: new packaging process with AIP | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-14163 | System Exploitation | Software Integration | 27/04/11 | Major | Accepted | Problem Report | Nomenclature Document doesn't contain IVV information | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-14103 | System Exploitation | Software Integration | 19/04/11 | Major | Verified | Problem Report | Why the header IVV is Ã©ronnÃ© in the documentation Mozart. | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-14037 | System Factory Validation | Software Integration | 12/04/11 | Minor | Analysed | Problem Report | XML <![CDATA]]> value badly serialized | orchestra the standard user for orchestra test |  |  |  | 08/08/11
ORC-13881 | System Exploitation |  | 30/03/11 | Major | Submitted | Enhancement Request | What link between the test sheets and the core Model Charm? | orchestra the standard user for orchestra test |  |  |  | 22/08/11
ORC-13850 | System Factory Validation | Software Integration | 29/03/11 | Minor | Closed | Problem Report | The expand on a test campaign (with a wrong path in IVV artifact) crashes the IVV connector | orchestra the standard user for orchestra test |  |  |  | 22/08/11
ORC-13781 | System Site Validation | Software Integration | 25/03/11 | Major | Closed | Problem Report | Problem with IVV Navigation that cause the framework to freeze | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-13775 | System Exploitation |  | 24/03/11 | Major | Closed | Problem Report | The connector must return an error when trying to manage test sheets version lower than V4.5 | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-13637 | System Experimentation | Coding | 16/03/11 | Minor | Closed | Problem Report | Could not deserialize status for command 'navigate' within implementation 'com.thalesgroup.orchestra.framework.connector.com. | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-13633 | Other | Coding | 16/03/11 | Minor | Closed | Problem Report | Status file issue on Navigate command | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-13520 | Software Integration | Coding | 09/03/11 | Minor | Closed | Enhancement Request | ConfdirIVV: change on PublicationContexts_description_Ivv.xml | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-13208 | Software Verification | Coding | 17/02/11 | Minor | Closed | Problem Report | Remove all smoved file prom project | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-13143 | System Factory Validation | Software Integration | 15/02/11 | Minor | Closed | Problem Report | Misunderstood error when i do a navigate on IVV artifact | orchestra the standard user for orchestra test |  |  |  | 10/05/11
ORC-13107 | System Factory Validation | Software Integration | 14/02/11 | Major | Closed | Problem Report | An error raised during Mozart project migration (to 3G) containing IVV artifacts | orchestra the standard user for orchestra test |  |  |  | 10/05/11
ORC-13062 | Software Integration |  | 10/02/11 | Minor | Closed | Problem Report | ConfdirIVV: the confdir doesn't respect the rule defined in prod47833 | orchestra the standard user for orchestra test |  |  |  | 12/04/11
ORC-12723 | Coding | Coding | 19/01/11 | Minor | Closed | Problem Report | Move files from ivv connector project to confdir | orchestra the standard user for orchestra test |  |  |  | 10/05/11
ORC-12582 | Coding | Coding | 07/01/11 | Minor | Closed | Problem Report | Check IVV Test sheet version from the IVV Connector | orchestra the standard user for orchestra test |  |  |  | 05/08/11
ORC-12569 | System Factory Validation | Software Integration | 06/01/11 | Minor | Closed | Problem Report | No IVV Types icon in the LM | orchestra the standard user for orchestra test |  |  |  | 03/03/11
ORC-12546 | Coding | Coding | 04/01/11 | Minor | Closed | Enhancement Request | Update the IVV Connector 5.0 | orchestra the standard user for orchestra test |  |  |  | 10/05/11
ORC-12473 | Software Integration | Other | 15/12/10 | Minor | Closed | Enhancement Request | Patch vm files from Confdir | orchestra the standard user for orchestra test |  |  |  | 10/05/11
ORC-12396 | System Factory Validation | Software Integration | 09/12/10 | Minor | Closed | Problem Report | Bad error message when the IVV Test Sheet is under a not supported format | orchestra the standard user for orchestra test |  |  |  | 05/08/11
ORC-12347 | System Factory Validation | Software Integration | 03/12/10 | Major | Closed | Problem Report | Unable to extract IVV artifact | orchestra the standard user for orchestra test |  |  |  | 05/08/11
ORC-12333 | Coding | Coding | 02/12/10 | Minor | Closed | Problem Report | Update the connector for phase renumbering format | orchestra the standard user for orchestra test |  |  |  | 10/05/11
ORC-12239 | Coding | Coding | 25/11/10 | Minor | Closed | Problem Report | Update the IVV Connector for new test sheet labels | orchestra the standard user for orchestra test |  |  |  | 10/05/11
ORC-12041 | Coding | Coding | 05/11/10 | Minor | Closed | Enhancement Request | Update IVV Connector for V4.5 | orchestra the standard user for orchestra test |  |  |  | 10/05/11
ORC-11853 | Coding | Coding | 18/10/10 | Minor | Closed | Enhancement Request | Update de IVV Connector for UID concept | orchestra the standard user for orchestra test |  |  |  | 19/10/10
ORC-11650 | Software Integration | Software Integration | 30/09/10 | Minor | Closed | Problem Report | Confdir Ivv v5: update | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-11647 | Software Integration |  | 30/09/10 | Minor | Closed | Problem Report | ConnectorIVV: update connector.gradle | orchestra the standard user for orchestra test |  |  |  | 12/04/11
ORC-11628 | System Exploitation | System Site Integration | 29/09/10 | Major | Closed | Enhancement Request | Adapt the IVV connector to the test sheet modifications for KP Prisme | orchestra the standard user for orchestra test |  |  |  | 24/03/11
ORC-11340 | System Exploitation | Coding | 08/09/10 | Major | Closed | Problem Report | Thest Sheet Identification should be extracted as a property for the test sheet header | orchestra the standard user for orchestra test |  |  |  | 10/05/11
ORC-11001 | System Exploitation |  | 29/07/10 | Major | Closed | Enhancement Request | Test Case Setup should be identified as "Setup" | orchestra the standard user for orchestra test |  |  |  | 01/03/11
ORC-10971 | Other |  | 23/07/10 | Minor | Closed | Problem Report | [ConnectorIVV] Error arise while installing ConnectorIVV through msi installer | orchestra the standard user for orchestra test |  |  |  | 29/07/10
ORC-10810 | Coding | Coding | 08/07/10 | Minor | Closed | Problem Report | Update the DLL used for the IVV Connector | orchestra the standard user for orchestra test |  |  |  | 10/05/11
ORC-10311 | System Factory Validation | Coding | 07/05/10 | Minor | Closed | Problem Report | extraction of a test sheet with only one empty test case => result of the extraction : 2 test cases are present | orchestra the standard user for orchestra test |  |  |  | 10/05/11
ORC-10185 | System Exploitation | Other | 20/04/10 | Major | Closed | Problem Report | [ConnectorIVV]: bad VDD deliverd in Orchestra 4.4 | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-10074 | System Site Integration |  | 13/04/10 | Minor | Closed | Problem Report | IVV onglet Test defects detail. IVV 4.1.6 20091120 Orchestra 4.3 | orchestra the standard user for orchestra test |  |  |  | 19/08/10
ORC-9996 | Other | Other | 07/04/10 | Minor | Closed | Enhancement Request | New function with link manager for test result | orchestra the standard user for orchestra test |  |  |  | 13/08/10
ORC-9878 | Software Integration | Other | 23/03/10 | Minor | Closed | Problem Report | IVV Connector should not delivers Orchestra DLL in its home directory | orchestra the standard user for orchestra test |  |  |  | 17/08/10
ORC-9854 | System Experimentation | Other | 22/03/10 | Major | Closed | Enhancement Request | The name of IVV artifact elements in the 'Assembler Explorer" is non-explicit | orchestra the standard user for orchestra test |  |  |  | 04/04/11
ORC-9695 | System Factory Validation |  | 11/03/10 | Minor | Closed | Problem Report | Not explicit error message when the .ivv contains not expected string | orchestra the standard user for orchestra test |  |  |  | 10/06/10
ORC-9605 | System Exploitation | Software Integration | 26/02/10 | Minor | Closed | Problem Report | The case of the first character of the confdir subfolders name are incoherents: "papeeteDoc" or "PapeeteDoc", ... | orchestra the standard user for orchestra test |  |  |  | 04/04/11
ORC-9591 | System Exploitation | Software Integration | 26/02/10 | Major | Verified | Problem Report | The case of the first character of the confdir subfolders name are incoherents: "papeeteDoc" or "PapeeteDoc", ... | orchestra the standard user for orchestra test |  |  |  | 10/08/11
ORC-9508 | Software Integration | Software Integration | 22/02/10 | Minor | Closed | Enhancement Request | migration script gradle | orchestra the standard user for orchestra test |  |  |  | 12/04/11
ORC-9376 | System Experimentation | Other | 11/02/10 | Major | Closed | Problem Report | The IVV connector cause Mozart publication error because of decimal values with commas instead of points | orchestra the standard user for orchestra test |  |  |  | 04/04/11
ORC-9212 | Other | Other | 01/02/10 | Major | Closed | Problem Report | Papeete Framework crash when attempting to extract an .ivv artefact | orchestra the standard user for orchestra test |  |  |  | 22/12/10
ORC-9210 | System Factory Validation | Coding | 01/02/10 | Minor | Closed | Enhancement Request | The .ivv used by the IVV connector should be created by the dashboard. | orchestra the standard user for orchestra test |  |  |  | 10/05/11
ORC-9187 | System Factory Validation | Software Integration | 28/01/10 | Blocking | Closed | Problem Report | Error during the extraction of IVV fragments | orchestra the standard user for orchestra test |  |  |  | 16/08/10
ORC-9186 | System Factory Validation |  | 28/01/10 | Minor | Closed | Problem Report | Error during the IVV extraction when a sheet is empty | orchestra the standard user for orchestra test |  |  |  | 10/06/10
ORC-9083 | System Exploitation |  | 20/01/10 | Major | Closed | Problem Report | Ref 264 - Major - Accent not supported by IVV connector | orchestra the standard user for orchestra test |  |  |  | 12/07/10
ORC-9073 | System Factory Validation |  | 19/01/10 | Major | Closed | Enhancement Request | The data imported from doors into the dashboard should be displayed. | orchestra the standard user for orchestra test |  |  |  | 29/07/10
ORC-8805 | Coding | Coding | 15/12/09 | Minor | Closed | Problem Report | Migrate IVV Connector Confdir for Orchestra 5.x versions | orchestra the standard user for orchestra test |  |  |  | 08/02/10
ORC-8804 | Coding | Coding | 15/12/09 | Minor | Closed | Enhancement Request | Migrate IVV connector Confdir for Orchestra 4.x | orchestra the standard user for orchestra test |  |  |  | 08/02/10
ORC-8802 | Coding | Coding | 15/12/09 | Minor | Closed | Enhancement Request | Migrate IVV Connector for products beta version | orchestra the standard user for orchestra test |  |  |  | 08/02/10
ORC-8290 | Other | Software Integration | 06/11/09 | Minor | Closed | Problem Report | Add Orchestra Dlls to Source Control | orchestra the standard user for orchestra test |  |  |  | 02/12/09
ORC-8261 | Other | Software Integration | 05/11/09 | Minor | Closed | Problem Report | Rebuild IVV Connector with new Orchestra Framework Library Version | orchestra the standard user for orchestra test |  |  |  | 02/12/09
ORC-8260 | System Site Validation | Software Integration | 05/11/09 | Major | Closed | Problem Report | Connector does not manage special character in Test Campaign folder path | orchestra the standard user for orchestra test |  |  |  | 02/07/10
ORC-8240 | Other | Other | 04/11/09 | Minor | Closed | Problem Report | Connector does not manage special caracter in path | orchestra the standard user for orchestra test |  |  |  | 11/02/10
ORC-7926 | Other | Other | 14/10/09 | Major | Closed | Problem Report | Display problem in Artifact Explorer if test sheet name contains a dot | orchestra the standard user for orchestra test |  |  |  | 08/02/10
ORC-7883 | Software Integration | Software Integration | 12/10/09 | Minor | Closed | Enhancement Request | Export Columns size through connector | orchestra the standard user for orchestra test |  |  |  | 08/02/10
ORC-7803 | Software Integration | Other | 06/10/09 | Minor | Closed | Enhancement Request | PapeeteIvvqConfdir: renommage du livrable | orchestra the standard user for orchestra test |  |  |  | 03/12/09
ORC-7779 | System Factory Validation | Software Integration | 02/10/09 | Minor | Closed | Problem Report | The list returned by the IVV connector is not alpha sorted | orchestra the standard user for orchestra test |  |  |  | 08/02/10
ORC-7645 | System Experimentation | Other | 23/09/09 | Minor | Closed | Enhancement Request | IVV Dashboard must be useable as artefact | orchestra the standard user for orchestra test |  |  |  | 10/05/11
ORC-7642 | System Exploitation | Software Integration | 23/09/09 | Major | Closed | Enhancement Request | IVV connector - It must be possible to select root IVV artefact (campaign) | orchestra the standard user for orchestra test |  |  |  | 05/10/10
ORC-7638 | System Factory Integration | Software Integration | 23/09/09 | Minor | Closed | Problem Report | Excel Automation Error when using Connector | orchestra the standard user for orchestra test |  |  |  | 06/10/09
ORC-7614 | Other | Other | 21/09/09 | Blocking | Closed | Problem Report | IVV Connector crashed when used with Papeete 3.10.3 | orchestra the standard user for orchestra test |  |  |  | 06/10/09
ORC-7513 | Software Integration | Software Integration | 09/09/09 | Major | Closed | Problem Report | Connector does not manage non english Test Sheets | orchestra the standard user for orchestra test |  |  |  | 06/10/09
ORC-7504 | Software Integration | Software Integration | 09/09/09 | Minor | Closed | Problem Report | Add autogenerated Id for Setup TestCase | orchestra the standard user for orchestra test |  |  |  | 06/10/09
ORC-7477 | Software Integration | Software Integration | 08/09/09 | Minor | Closed | Problem Report | Error on Documentary Export with Empty Test Sheet | orchestra the standard user for orchestra test |  |  |  | 06/10/09
ORC-7444 | Software Integration | Software Integration | 04/09/09 | Minor | Closed | Enhancement Request | Remove GeneralProvider publication for headers | orchestra the standard user for orchestra test |  |  |  | 06/10/09
ORC-7436 | Other | Other | 04/09/09 | Minor | Closed | Enhancement Request | Add trace mod for Connector | orchestra the standard user for orchestra test |  |  |  | 06/10/09
ORC-7425 | Coding | Other | 03/09/09 | Minor | Closed | Problem Report | Modify Excel Object Declaration | orchestra the standard user for orchestra test |  |  |  | 06/10/09